## KPI Input
Throughputs / shift: | [23 empty] | WIP Levels
|  | Launch | Type | PAA | Type | BR1 | Type | Precure | Type | GKN OX | Type | TAI | Type | SET OX | Type | PWA OX | Type | BL Scan | Type | EQN Submission | Type | Delivery | Type | GKN | SET | Peening | XRI | IHC | PWA | QN Processing
1st | 2015-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Wed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Thu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Fri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Wed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Thu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Fri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Wed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Thu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Fri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Wed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Thu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Fri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Sun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Mon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Tue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Wed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st | 2015-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd | Thu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Charts
|  |  | Average Days to plan | -5.4238
|  |  | Average Blades to Plan | -88.625
MTD Status Compared to Build Plan
Number of Days | -4.4667 | Days
Number of Blades | -67 | PCS
% to schedule | 62.78%
MTD Status Compared to Build Plan
Number of Days | -10 | Days
Number of Blades | -100 | PCS
% to schedule | 16.67%
MTD Status Compared to Build Plan
Number of Days | -4.1333 | Days
Number of Blades | -62 | PCS
% to schedule | 65.56%
MTD Status Compared to Build Plan
Number of Days | -4.64 | Days
Number of Blades | -87 | PCS
% to schedule | 61.33%
MTD Status Compared to Build Plan
Number of Days | -6.85 | Days
Number of Blades | -137 | PCS
% to schedule | 42.92%
MTD Status Compared to Build Plan
Number of Days | -2 | Days
Number of Blades | -30 | PCS
% to schedule | 83.33%
MTD Status Compared to Build Plan
Number of Days | -7.75 | Days
Number of Blades | -155 | PCS
% to schedule | 35.42%
MTD Status Compared to Build Plan
Number of Days | -3.55 | Days
Number of Blades | -71 | PCS
% to schedule | 35.42%
MTD Status Compared to Build Plan
Number of Days | -4.75 | Days
Number of Blades | -95 | PCS
% to schedule | 60.42%
MTD Status Compared to Build Plan
Number of Days | -3.4 | Days
Number of Blades | -51 | PCS
% to schedule | 71.67%

## Ramp Plan
|  | 20 | 20
| Engine Sets / Month | Blades / Month | Blades / Day
Launch | 15 | 375 | 18.75 | 25
PAA | 15 | 375 | 18.75 | 25
BR1 | 15 | 375 | 18.75 | 25
Precure | 15 | 375 | 18.75 | 25
GKN OX/hand abrade | 15 | 375 | 18.75 | 25
TAI | 15 | 375 | 18.75 | 25
SET OX | 15 | 375 | 18.75 | 25
PWA OX | 12 | 300 | 15 | 25
EQN Submission | 12 | 300 | 15 | 25
Delivery | 10 | 200 | 10 | 20

## 30K Launch
| Launch |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 21
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 12 | 12 | -4.4 | -88 | 12% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 16 | 28 | -4.6 | -92 | 23.33% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 0 | 28 | -5.6 | -112 | 20% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 24 | 52 | -5.4 | -108 | 32.5% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 26 | 78 | -4.1 | -82 | 48.75% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 0 | 78 | -4.1 | -82 | 48.75% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 1 | 79 | -5.05 | -101 | 43.89% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 0 | 79 | -7.05 | -141 | 35.91% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 16 | 95 | -7.25 | -145 | 39.58% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 24 | 119 | -7.05 | -141 | 45.77% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 | 26 | 145 | -6.75 | -135 | 51.79% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 145 | -6.75 | -135 | 51.79% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 145 | -6.75 | -135 | 51.79% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 145 | -7.75 | -155 | 48.33% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 145 | -9.75 | -195 | 42.65% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 145 | -10.75 | -215 | 40.28% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 145 | -11.75 | -235 | 38.16% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 145 | -12.75 | -255 | 36.25% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 145 | -12.75 | -255 | 36.25% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 145 | -12.75 | -255 | 36.25% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 145 | -12.75 | -255 | 36.25% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 145 | -12.75 | -255 | 36.25% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 145 | -13.75 | -275 | 34.52% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 145 | -14.75 | -295 | 32.95% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 145 | -15.75 | -315 | 31.52% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 145 | -15.75 | -315 | 31.52% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 145 | -15.75 | -315 | 31.52% | 0
#REF! | [6 empty] | 240 | 145 |  | -4.75 | -95 | 60.42%
0%
Formulas:
Today = IF([Launch]=TODAY(),1,0)

## BA Launch
| Launch |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 21
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | BA Build Plan | BA Actual | BA Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 0 | 0 | -5 | -100 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 0 | 0 | -6 | -120 | 0% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 3 | 3 | -6.85 | -137 | 2.143% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 0 | 3 | -7.85 | -157 | 1.875% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 0 | 3 | -7.85 | -157 | 1.875% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 0 | 3 | -7.85 | -157 | 1.875% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 0 | 3 | -8.85 | -177 | 1.667% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 0 | 3 | -10.85 | -217 | 1.364% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 0 | 3 | -11.85 | -237 | 1.25% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 0 | 3 | -12.85 | -257 | 1.154% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 |  | 3 | -13.85 | -277 | 1.071% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 3 | -13.85 | -277 | 1.071% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 3 | -13.85 | -277 | 1.071% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 3 | -14.85 | -297 | 1% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 3 | -16.85 | -337 | 0.8824% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 3 | -17.85 | -357 | 0.8333% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 3 | -18.85 | -377 | 0.7895% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 3 | -19.85 | -397 | 0.75% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 3 | -19.85 | -397 | 0.75% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 3 | -19.85 | -397 | 0.75% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 3 | -19.85 | -397 | 0.75% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 3 | -19.85 | -397 | 0.75% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 3 | -20.85 | -417 | 0.7143% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 3 | -21.85 | -437 | 0.6818% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 3 | -22.85 | -457 | 0.6522% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 3 | -22.85 | -457 | 0.6522% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 3 | -22.85 | -457 | 0.6522% | 0
#REF! | [6 empty] | 240 | 3 |  | -11.85 | -237 | 1.25%
0%
Formulas:
Today = IF([Launch]=TODAY(),1,0)

## PAA 30K
| 30K PAA |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 6 | 6 | -4.7 | -94 | 6% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 13 | 19 | -5.05 | -101 | 15.83% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 7 | 26 | -5.7 | -114 | 18.57% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 19 | 45 | -5.75 | -115 | 28.12% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 11 | 56 | -5.2 | -104 | 35% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 8 | 64 | -4.8 | -96 | 40% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 29 | 93 | -4.35 | -87 | 51.67% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 11 | 104 | -5.8 | -116 | 47.27% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 19 | 123 | -5.85 | -117 | 51.25% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 23 | 146 | -5.7 | -114 | 56.15% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 | 23 | 169 | -5.55 | -111 | 60.36% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 169 | -5.55 | -111 | 60.36% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 169 | -5.55 | -111 | 60.36% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 169 | -6.55 | -131 | 56.33% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 169 | -8.55 | -171 | 49.71% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 169 | -9.55 | -191 | 46.94% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 169 | -10.55 | -211 | 44.47% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 169 | -11.55 | -231 | 42.25% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 169 | -11.55 | -231 | 42.25% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 169 | -11.55 | -231 | 42.25% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 169 | -11.55 | -231 | 42.25% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 169 | -11.55 | -231 | 42.25% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 169 | -12.55 | -251 | 40.24% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 169 | -13.55 | -271 | 38.41% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 169 | -14.55 | -291 | 36.74% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 169 | -14.55 | -291 | 36.74% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 169 | -14.55 | -291 | 36.74% | 0
#REF! | [6 empty] | 240 | 169 |  | -3.55 | -71 | 70.42%
0
Formulas:
Today = IF([Date]=TODAY(),1,0)

## PAA BA
| BA PAA |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | BA Build Plan | BA Actual | BA Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 0 | 0 | -5 | -100 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 0 | 0 | -6 | -120 | 0% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 3 | 3 | -6.85 | -137 | 2.143% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 0 | 3 | -7.85 | -157 | 1.875% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 0 | 3 | -7.85 | -157 | 1.875% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 0 | 3 | -7.85 | -157 | 1.875% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 0 | 3 | -8.85 | -177 | 1.667% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 0 | 3 | -10.85 | -217 | 1.364% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 0 | 3 | -11.85 | -237 | 1.25% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 0 | 3 | -12.85 | -257 | 1.154% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 |  | 3 | -13.85 | -277 | 1.071% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 3 | -13.85 | -277 | 1.071% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 3 | -13.85 | -277 | 1.071% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 3 | -14.85 | -297 | 1% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 3 | -16.85 | -337 | 0.8824% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 3 | -17.85 | -357 | 0.8333% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 3 | -18.85 | -377 | 0.7895% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 3 | -19.85 | -397 | 0.75% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 3 | -19.85 | -397 | 0.75% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 3 | -19.85 | -397 | 0.75% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 3 | -19.85 | -397 | 0.75% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 3 | -19.85 | -397 | 0.75% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 3 | -20.85 | -417 | 0.7143% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 3 | -21.85 | -437 | 0.6818% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 3 | -22.85 | -457 | 0.6522% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 3 | -22.85 | -457 | 0.6522% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 3 | -22.85 | -457 | 0.6522% | 0
#REF! | [6 empty] | 240 | 3 |  | -11.85 | -237 | 1.25%
0
Formulas:
Today = IF([BA PAA]=TODAY(),1,0)

## PAA MRJ
| MRJ PAA |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | MRJ Build Plan | MRJ Actual | MRJ Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 0 | 0 | -5 | -100 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 0 | 0 | -6 | -120 | 0% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 0 | 0 | -7 | -140 | 0% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 0 | 0 | -8 | -160 | 0% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 0 | 0 | -8 | -160 | 0% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 0 | 0 | -8 | -160 | 0% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 0 | 0 | -9 | -180 | 0% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 0 | 0 | -11 | -220 | 0% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 0 | 0 | -12 | -240 | 0% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 0 | 0 | -13 | -260 | 0% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 |  | 0 | -14 | -280 | 0% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 0 | -14 | -280 | 0% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 0 | -14 | -280 | 0% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 0 | -15 | -300 | 0% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 0 | -17 | -340 | 0% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 0 | -18 | -360 | 0% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 0 | -19 | -380 | 0% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 0 | -20 | -400 | 0% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 0 | -20 | -400 | 0% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 0 | -20 | -400 | 0% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 0 | -20 | -400 | 0% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 0 | -20 | -400 | 0% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 0 | -21 | -420 | 0% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 0 | -22 | -440 | 0% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 0 | -23 | -460 | 0% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 0 | -23 | -460 | 0% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 0 | -23 | -460 | 0% | 0
#REF! | [6 empty] | 240 | 0 |  | -12 | -240 | 0%
0
Formulas:
Today = IF([MRJ PAA]=TODAY(),1,0)

## BR1 30K
| BR1 |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 1 | 1 | -4.95 | -99 | 1% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 2 | 3 | -5.85 | -117 | 2.5% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 6 | 9 | -6.55 | -131 | 6.429% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 4 | 13 | -7.35 | -147 | 8.125% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 0 | 13 | -7.35 | -147 | 8.125% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 9 | 22 | -6.9 | -138 | 13.75% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 12 | 34 | -7.3 | -146 | 18.89% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 12 | 46 | -8.7 | -174 | 20.91% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 15 | 61 | -8.95 | -179 | 25.42% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 13 | 74 | -9.3 | -186 | 28.46% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 | 11 | 85 | -9.75 | -195 | 30.36% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 85 | -9.75 | -195 | 30.36% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 85 | -9.75 | -195 | 30.36% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 85 | -10.75 | -215 | 28.33% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 85 | -12.75 | -255 | 25% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 85 | -13.75 | -275 | 23.61% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 85 | -14.75 | -295 | 22.37% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 85 | -15.75 | -315 | 21.25% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 85 | -15.75 | -315 | 21.25% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 85 | -15.75 | -315 | 21.25% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 85 | -15.75 | -315 | 21.25% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 85 | -15.75 | -315 | 21.25% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 85 | -16.75 | -335 | 20.24% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 85 | -17.75 | -355 | 19.32% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 85 | -18.75 | -375 | 18.48% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 85 | -18.75 | -375 | 18.48% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 85 | -18.75 | -375 | 18.48% | 0
#REF! | [6 empty] | 240 | 85 |  | -7.75 | -155 | 35.42%
0
Formulas:
Today = IF([BR1]=TODAY(),1,0)

## TAI 30K
| TAI |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 13 | 13 | -1.35 | -27 | 32.5% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 15 | 28 | -3.6 | -72 | 28% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 4 | 32 | -4.4 | -88 | 26.67% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 0 | 32 | -5.4 | -108 | 22.86% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 15 | 47 | -5.65 | -113 | 29.38% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 0 | 47 | -5.65 | -113 | 29.38% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 0 | 47 | -5.65 | -113 | 29.38% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 13 | 60 | -6 | -120 | 33.33% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 10 | 70 | -7.5 | -150 | 31.82% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 11 | 81 | -7.95 | -159 | 33.75% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 12 | 93 | -8.35 | -167 | 35.77% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 | 10 | 103 | -8.85 | -177 | 36.79% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 103 | -8.85 | -177 | 36.79% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 103 | -8.85 | -177 | 36.79% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 103 | -9.85 | -197 | 34.33% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 103 | -11.85 | -237 | 30.29% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 103 | -12.85 | -257 | 28.61% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 103 | -13.85 | -277 | 27.11% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 103 | -14.85 | -297 | 25.75% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 103 | -14.85 | -297 | 25.75% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 103 | -14.85 | -297 | 25.75% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 103 | -14.85 | -297 | 25.75% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 103 | -14.85 | -297 | 25.75% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 103 | -15.85 | -317 | 24.52% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 103 | -16.85 | -337 | 23.41% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 103 | -17.85 | -357 | 22.39% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 103 | -17.85 | -357 | 22.39% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 103 | -17.85 | -357 | 22.39% | 0
#REF! | [6 empty] | 240 | 103 |  | -6.85 | -137 | 42.92%
0
Formulas:
Today = IF([TAI]=TODAY(),1,0)

## TAI BA
| BA TAI |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
20
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | BA Build Plan | BA Actual | BA Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 20 | 20 | 20 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 20 | 20 | 0 | 0 | 0 | -1 | -20 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 40 | 20 | 20 | 0 | 0 | -2 | -40 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 100 | 20 | 20 | 0 | 0 | -5 | -100 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 120 | 20 | 20 | 8 | 8 | -5.6 | -112 | 6.667% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 140 | 20 | 20 | 0 | 8 | -6.6 | -132 | 5.714% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 160 | 20 | 20 | 0 | 8 | -7.6 | -152 | 5% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 160 | 20 | 0 | 0 | 8 | -7.6 | -152 | 5% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 160 | 20 | 0 | 0 | 8 | -7.6 | -152 | 5% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 180 | 20 | 20 | 0 | 8 | -8.6 | -172 | 4.444% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 220 | 20 | 20 | 0 | 8 | -10.6 | -212 | 3.636% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 240 | 20 | 20 | 0 | 8 | -11.6 | -232 | 3.333% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 260 | 20 | 20 | 3 | 11 | -12.45 | -249 | 4.231% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 280 | 20 | 20 |  | 11 | -13.45 | -269 | 3.929% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 280 | 20 | 0 |  | 11 | -13.45 | -269 | 3.929% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 280 | 20 | 0 |  | 11 | -13.45 | -269 | 3.929% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 300 | 20 | 20 |  | 11 | -14.45 | -289 | 3.667% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 340 | 20 | 20 |  | 11 | -16.45 | -329 | 3.235% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 360 | 20 | 20 |  | 11 | -17.45 | -349 | 3.056% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 380 | 20 | 20 |  | 11 | -18.45 | -369 | 2.895% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 400 | 20 | 20 |  | 11 | -19.45 | -389 | 2.75% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 400 | 20 | 0 |  | 11 | -19.45 | -389 | 2.75% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 400 | 20 | 0 |  | 11 | -19.45 | -389 | 2.75% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 400 | 20 | 0 |  | 11 | -19.45 | -389 | 2.75% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 400 | 20 | 20 |  | 11 | -19.45 | -389 | 2.75% | 0
1 | 2016-01-27 | Wed | 27 | 21 | 420 | 20 | 20 |  | 11 | -20.45 | -409 | 2.619% | 0
1 | 2016-01-28 | Thu | 28 | 22 | 440 | 20 | 20 |  | 11 | -21.45 | -429 | 2.5% | 0
1 | 2016-01-29 | Fri | 29 | 23 | 460 | 20 | 20 |  | 11 | -22.45 | -449 | 2.391% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 460 | 20 | 0 |  | 11 | -22.45 | -449 | 2.391% | 0
0 | 2016-01-31 | Sun | 31 | 23 | 460 | 20 | 0 |  | 11 | -22.45 | -449 | 2.391% | 0
#REF! | [6 empty] | 240 | 11 |  | -11.45 | -229 | 4.583%
0
Formulas:
Today = IF([BA TAI]=TODAY(),1,0)

## SET OX 30K
| 30K SET OX |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
18.75
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 18.75 | 18.75 | 18.75 | 0 | 0 | -1 | -18.75 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 18.75 | 18.75 | 0 | 0 | 0 | -1 | -18.75 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 18.75 | 19 | 0 | 0 | 0 | -1 | -18.75 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 37.5 | 19 | 18.75 | 30 | 30 | -0.4 | -7.5 | 80% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 93.75 | 18.75 | 18.75 | 18 | 48 | -2.44 | -45.75 | 51.2% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 112.5 | 18.75 | 18.75 | 18 | 66 | -2.48 | -46.5 | 58.67% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 131.25 | 18.75 | 18.75 | 5 | 71 | -3.2133 | -60.25 | 54.1% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 150 | 18.75 | 18.75 | 5 | 76 | -3.9467 | -74 | 50.67% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 150 | 18.75 | 0 | 0 | 76 | -3.9467 | -74 | 50.67% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 150 | 19 | 0 | 0 | 76 | -3.9467 | -74 | 50.67% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 168.75 | 19 | 18.75 | 18 | 94 | -3.9867 | -74.75 | 55.7% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 206.25 | 18.75 | 18.75 | 12 | 106 | -5.3467 | -100.25 | 51.39% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 225 | 18.75 | 18.75 | 12 | 118 | -5.7067 | -107 | 52.44% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 243.75 | 18.75 | 18.75 | 0 | 118 | -6.7067 | -125.75 | 48.41% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 262.5 | 18.75 | 18.75 | 20 | 138 | -6.64 | -124.5 | 52.57% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 262.5 | 18.75 | 0 |  | 138 | -6.64 | -124.5 | 52.57% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 262.5 | 19 | 0 |  | 138 | -6.64 | -124.5 | 52.57% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 281.25 | 19 | 18.75 |  | 138 | -7.64 | -143.25 | 49.07% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 318.75 | 18.75 | 18.75 |  | 138 | -9.64 | -180.75 | 43.29% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 337.5 | 18.75 | 18.75 |  | 138 | -10.64 | -199.5 | 40.89% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 356.25 | 18.75 | 18.75 |  | 138 | -11.64 | -218.25 | 38.74% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 375 | 18.75 | 18.75 |  | 138 | -12.64 | -237 | 36.8% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 375 | 18.75 | 0 |  | 138 | -12.64 | -237 | 36.8% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 375 | 19 | 0 |  | 138 | -12.64 | -237 | 36.8% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 375 | 19 | 18.75 |  | 138 | -12.64 | -237 | 36.8% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 393.75 | 18.75 | 18.75 |  | 138 | -13.64 | -255.75 | 35.05% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 412.5 | 18.75 | 18.75 |  | 138 | -14.64 | -274.5 | 33.45% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 431.25 | 18.75 | 18.75 |  | 138 | -15.64 | -293.25 | 32% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 450 | 18.75 | 18.75 |  | 138 | -16.64 | -312 | 30.67% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 450 | 18.75 | 0 |  | 138 | -16.64 | -312 | 30.67% | 0
0 | 2016-01-31 | Sun | 31 | 24 | 450 | 18.75 | 0 |  | 138 | -16.64 | -312 | 30.67% | 0
[7 empty] | 225 | 138 |  | -4.64 | -87 | 61.33%
Formulas:
Today = IF([Date]=TODAY(),1,0)

## SET OX BA
| BA SET OX |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
18.75
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | BA Build Plan | BA Actual | BA Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 18.75 | 18.75 | 18.75 | 0 | 0 | -1 | -18.75 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 18.75 | 18.75 | 0 | 0 | 0 | -1 | -18.75 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 18.75 | 19 | 0 | 0 | 0 | -1 | -18.75 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 37.5 | 19 | 18.75 | 0 | 0 | -2 | -37.5 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 93.75 | 18.75 | 18.75 | 6 | 6 | -4.68 | -87.75 | 6.4% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 112.5 | 18.75 | 18.75 | 0 | 6 | -5.68 | -106.5 | 5.333% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 131.25 | 18.75 | 18.75 | 7 | 13 | -6.3067 | -118.25 | 9.905% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 150 | 18.75 | 18.75 | 0 | 13 | -7.3067 | -137 | 8.667% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 150 | 18.75 | 0 | 0 | 13 | -7.3067 | -137 | 8.667% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 150 | 19 | 0 | 0 | 13 | -7.3067 | -137 | 8.667% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 168.75 | 19 | 18.75 | 0 | 13 | -8.3067 | -155.75 | 7.704% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 206.25 | 18.75 | 18.75 | 0 | 13 | -10.3067 | -193.25 | 6.303% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 225 | 18.75 | 18.75 | 0 | 13 | -11.3067 | -212 | 5.778% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 243.75 | 18.75 | 18.75 | 0 | 13 | -12.3067 | -230.75 | 5.333% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 262.5 | 18.75 | 18.75 |  | 13 | -13.3067 | -249.5 | 4.952% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 262.5 | 18.75 | 0 |  | 13 | -13.3067 | -249.5 | 4.952% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 262.5 | 19 | 0 |  | 13 | -13.3067 | -249.5 | 4.952% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 281.25 | 19 | 18.75 |  | 13 | -14.3067 | -268.25 | 4.622% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 318.75 | 18.75 | 18.75 |  | 13 | -16.3067 | -305.75 | 4.078% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 337.5 | 18.75 | 18.75 |  | 13 | -17.3067 | -324.5 | 3.852% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 356.25 | 18.75 | 18.75 |  | 13 | -18.3067 | -343.25 | 3.649% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 375 | 18.75 | 18.75 |  | 13 | -19.3067 | -362 | 3.467% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 375 | 18.75 | 0 |  | 13 | -19.3067 | -362 | 3.467% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 375 | 19 | 0 |  | 13 | -19.3067 | -362 | 3.467% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 375 | 19 | 18.75 |  | 13 | -19.3067 | -362 | 3.467% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 393.75 | 18.75 | 18.75 |  | 13 | -20.3067 | -380.75 | 3.302% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 412.5 | 18.75 | 18.75 |  | 13 | -21.3067 | -399.5 | 3.152% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 431.25 | 18.75 | 18.75 |  | 13 | -22.3067 | -418.25 | 3.014% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 450 | 18.75 | 18.75 |  | 13 | -23.3067 | -437 | 2.889% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 450 | 18.75 | 0 |  | 13 | -23.3067 | -437 | 2.889% | 0
0 | 2016-01-31 | Sun | 31 | 24 | 450 | 18.75 | 0 |  | 13 | -23.3067 | -437 | 2.889% | 0
[7 empty] | 225 | 13 |  | -11.3067 | -212 | 5.778%
Formulas:
Today = IF([BA SET OX]=TODAY(),1,0)

## XRI OX 30K
| XRI OX |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
15
Weekday | Date | Jan | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 15 | 15 | 15 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 15 | 15 | 0 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 15 | 15 | 0 | 0 | 0 | -1 | -15 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 30 | 15 | 15 | 23 | 23 | -0.46667 | -7 | 76.67% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 75 | 15 | 15 | 7 | 30 | -3 | -45 | 40% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 90 | 15 | 15 | 11 | 41 | -3.2667 | -49 | 45.56% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 105 | 15 | 15 | 12 | 53 | -3.4667 | -52 | 50.48% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 120 | 15 | 15 | 14 | 67 | -3.5333 | -53 | 55.83% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 120 | 15 | 0 | 12 | 79 | -2.7333 | -41 | 65.83% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 120 | 15 | 0 | 12 | 91 | -1.9333 | -29 | 75.83% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 135 | 15 | 15 | 6 | 97 | -2.5333 | -38 | 71.85% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 165 | 15 | 15 | 18 | 115 | -3.3333 | -50 | 69.7% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 180 | 15 | 15 | 14 | 129 | -3.4 | -51 | 71.67% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 195 | 15 | 15 | 5 | 134 | -4.0667 | -61 | 68.72% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 210 | 15 | 15 | 16 | 150 | -4 | -60 | 71.43% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 210 | 15 | 0 |  | 150 | -4 | -60 | 71.43% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 210 | 15 | 0 |  | 150 | -4 | -60 | 71.43% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 225 | 15 | 15 |  | 150 | -5 | -75 | 66.67% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 255 | 15 | 15 |  | 150 | -7 | -105 | 58.82% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 270 | 15 | 15 |  | 150 | -8 | -120 | 55.56% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 285 | 15 | 15 |  | 150 | -9 | -135 | 52.63% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 300 | 15 | 15 |  | 150 | -10 | -150 | 50% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 300 | 15 | 0 |  | 150 | -10 | -150 | 50% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 300 | 15 | 0 |  | 150 | -10 | -150 | 50% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 300 | 15 | 15 |  | 150 | -10 | -150 | 50% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 315 | 15 | 15 |  | 150 | -11 | -165 | 47.62% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 330 | 15 | 15 |  | 150 | -12 | -180 | 45.45% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 345 | 15 | 15 |  | 150 | -13 | -195 | 43.48% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 360 | 15 | 15 |  | 150 | -14 | -210 | 41.67% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 360 | 15 | 0 |  | 150 | -14 | -210 | 41.67% | 0
0 | 2016-01-31 | Sun | 31 | 24 | 360 | 15 | 0 |  | 150 | -14 | -210 | 41.67% | 0
[7 empty] | 180 | 150 |  | -2 | -30 | 83.33%
Formulas:
Today = IF([XRI OX]=TODAY(),1,0)

## PWA OX 30K
| PWA OX |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 300 |  |  |  | 24
Daily Flow Rate
15
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 15 | 15 | 15 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 15 | 15 | 0 | 12 | 12 | -0.2 | -3 | 80% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 15 | 15 | 0 | 0 | 12 | -0.2 | -3 | 80% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 30 | 15 | 15 | 30 | 42 | 0.8 | 12 | 140% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 75 | 15 | 15 | 0 | 42 | -2.2 | -33 | 56% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 90 | 15 | 15 | 4 | 46 | -2.9333 | -44 | 51.11% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 105 | 15 | 15 | 0 | 46 | -3.9333 | -59 | 43.81% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 120 | 15 | 15 | 14 | 60 | -4 | -60 | 50% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 120 | 15 | 0 | 11 | 71 | -3.2667 | -49 | 59.17% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 120 | 15 | 0 | 0 | 71 | -3.2667 | -49 | 59.17% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 135 | 15 | 15 | 0 | 71 | -4.2667 | -64 | 52.59% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 165 | 15 | 15 | 0 | 71 | -6.2667 | -94 | 43.03% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 180 | 15 | 15 | 30 | 101 | -5.2667 | -79 | 56.11% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 195 | 15 | 15 | 12 | 113 | -5.4667 | -82 | 57.95% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 210 | 15 | 15 | 5 | 118 | -6.1333 | -92 | 56.19% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 210 | 15 | 0 |  | 118 | -6.1333 | -92 | 56.19% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 210 | 15 | 0 |  | 118 | -6.1333 | -92 | 56.19% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 225 | 15 | 15 |  | 118 | -7.1333 | -107 | 52.44% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 255 | 15 | 15 |  | 118 | -9.1333 | -137 | 46.27% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 270 | 15 | 15 |  | 118 | -10.1333 | -152 | 43.7% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 285 | 15 | 15 |  | 118 | -11.1333 | -167 | 41.4% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 300 | 15 | 15 |  | 118 | -12.1333 | -182 | 39.33% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 300 | 15 | 0 |  | 118 | -12.1333 | -182 | 39.33% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 300 | 15 | 0 |  | 118 | -12.1333 | -182 | 39.33% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 300 | 15 | 15 |  | 118 | -12.1333 | -182 | 39.33% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 315 | 15 | 15 |  | 118 | -13.1333 | -197 | 37.46% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 330 | 15 | 15 |  | 118 | -14.1333 | -212 | 35.76% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 345 | 15 | 15 |  | 118 | -15.1333 | -227 | 34.2% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 360 | 15 | 15 |  | 118 | -16.1333 | -242 | 32.78% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 360 | 15 | 13 |  | 118 | -16.1333 | -242 | 32.78% | 0
0 | 2016-01-31 | Sun. | 31 | 24 | 360 | 15 | 13 |  | 118 | -16.1333 | -242 | 32.78% | 0
[7 empty] | 180 | 118 |  | -4.1333 | -62 | 65.56%
Formulas:
Today = IF([PWA OX]=TODAY(),1,0)

## PWA OX BA
| PWA OX |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 300 |  |  |  | 24
Daily Flow Rate
15
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | BA Build Plan | BA Actual | BA Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 15 | 15 | 15 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 15 | 15 | 0 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 15 | 15 | 0 | 0 | 0 | -1 | -15 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 30 | 15 | 15 | 0 | 0 | -2 | -30 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 75 | 15 | 15 | 0 | 0 | -5 | -75 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 90 | 15 | 15 | 0 | 0 | -6 | -90 | 0% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 105 | 15 | 15 | 0 | 0 | -7 | -105 | 0% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 120 | 15 | 15 | 1 | 1 | -7.9333 | -119 | 0.8333% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 120 | 15 | 0 | 0 | 1 | -7.9333 | -119 | 0.8333% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 120 | 15 | 0 | 0 | 1 | -7.9333 | -119 | 0.8333% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 135 | 15 | 15 | 0 | 1 | -8.9333 | -134 | 0.7407% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 165 | 15 | 15 | 0 | 1 | -10.9333 | -164 | 0.6061% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 180 | 15 | 15 | 1 | 2 | -11.8667 | -178 | 1.111% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 195 | 15 | 15 | 0 | 2 | -12.8667 | -193 | 1.026% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 210 | 15 | 15 |  | 2 | -13.8667 | -208 | 0.9524% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 210 | 15 | 0 |  | 2 | -13.8667 | -208 | 0.9524% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 210 | 15 | 0 |  | 2 | -13.8667 | -208 | 0.9524% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 225 | 15 | 15 |  | 2 | -14.8667 | -223 | 0.8889% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 255 | 15 | 15 |  | 2 | -16.8667 | -253 | 0.7843% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 270 | 15 | 15 |  | 2 | -17.8667 | -268 | 0.7407% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 285 | 15 | 15 |  | 2 | -18.8667 | -283 | 0.7018% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 300 | 15 | 15 |  | 2 | -19.8667 | -298 | 0.6667% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 300 | 15 | 0 |  | 2 | -19.8667 | -298 | 0.6667% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 300 | 15 | 0 |  | 2 | -19.8667 | -298 | 0.6667% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 300 | 15 | 15 |  | 2 | -19.8667 | -298 | 0.6667% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 315 | 15 | 15 |  | 2 | -20.8667 | -313 | 0.6349% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 330 | 15 | 15 |  | 2 | -21.8667 | -328 | 0.6061% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 345 | 15 | 15 |  | 2 | -22.8667 | -343 | 0.5797% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 360 | 15 | 15 |  | 2 | -23.8667 | -358 | 0.5556% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 360 | 15 | 13 |  | 2 | -23.8667 | -358 | 0.5556% | 0
0 | 2016-01-31 | Sun. | 31 | 24 | 360 | 15 | 13 |  | 2 | -23.8667 | -358 | 0.5556% | 0
[7 empty] | 180 | 2 |  | -11.8667 | -178 | 1.111%
Formulas:
Today = IF([PWA OX]=TODAY(),1,0)

## Blue Light 30K
| Blue Light |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
15
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 15 | 15 | 15 | 19 | 19 | 0.26667 | 4 | 126.7% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 15 | 15 | 0 | 11 | 30 | 1 | 15 | 200% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 15 | 15 | 0 |  | 30 | 1 | 15 | 200% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 30 | 15 | 15 | 1 | 31 | 0.066667 | 1 | 103.3% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 75 | 15 | 15 | 3 | 34 | -2.7333 | -41 | 45.33% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 90 | 15 | 15 | 10 | 44 | -3.0667 | -46 | 48.89% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 105 | 15 | 15 | 6 | 50 | -3.6667 | -55 | 47.62% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 120 | 15 | 15 | 12 | 62 | -3.8667 | -58 | 51.67% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 120 | 15 | 0 | 22 | 84 | -2.4 | -36 | 70% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 120 | 15 | 0 | 5 | 89 | -2.0667 | -31 | 74.17% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 135 | 15 | 15 | 1 | 90 | -3 | -45 | 66.67% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 165 | 15 | 15 | 0 | 90 | -5 | -75 | 54.55% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 180 | 15 | 15 | 19 | 109 | -4.7333 | -71 | 60.56% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 195 | 15 | 15 | 12 | 121 | -4.9333 | -74 | 62.05% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 210 | 15 | 15 | 8 | 129 | -5.4 | -81 | 61.43% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 210 | 15 | 0 |  | 129 | -5.4 | -81 | 61.43% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 210 | 15 | 0 |  | 129 | -5.4 | -81 | 61.43% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 225 | 15 | 15 |  | 129 | -6.4 | -96 | 57.33% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 255 | 15 | 15 |  | 129 | -8.4 | -126 | 50.59% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 270 | 15 | 15 |  | 129 | -9.4 | -141 | 47.78% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 285 | 15 | 15 |  | 129 | -10.4 | -156 | 45.26% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 300 | 15 | 15 |  | 129 | -11.4 | -171 | 43% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 300 | 15 | 0 |  | 129 | -11.4 | -171 | 43% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 300 | 15 | 0 |  | 129 | -11.4 | -171 | 43% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 300 | 15 | 15 |  | 129 | -11.4 | -171 | 43% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 315 | 15 | 15 |  | 129 | -12.4 | -186 | 40.95% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 330 | 15 | 15 |  | 129 | -13.4 | -201 | 39.09% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 345 | 15 | 15 |  | 129 | -14.4 | -216 | 37.39% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 360 | 15 | 15 |  | 129 | -15.4 | -231 | 35.83% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 360 | 15 | 0 |  | 129 | -15.4 | -231 | 35.83% | 0
0 | 2016-01-31 | Sun | 31 | 24 | 360 | 15 | 0 |  | 129 | -15.4 | -231 | 35.83% | 0
[7 empty] | 180 | 129 |  | -3.4 | -51 | 71.67%
315
Formulas:
Today = IF([Blue Light]=TODAY(),1,0)

## Blue Light BA
| Blue Light |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 375 |  |  |  | 24
Daily Flow Rate
15
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | BA Build Plan | BA Actual | BA Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 15 | 15 | 15 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 15 | 15 | 0 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 15 | 15 | 0 | 0 | 0 | -1 | -15 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 30 | 15 | 15 | 0 | 0 | -2 | -30 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 75 | 15 | 15 | 0 | 0 | -5 | -75 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 6 | 90 | 15 | 15 | 0 | 0 | -6 | -90 | 0% | 0
1 | 2016-01-07 | Thu | 07 | 7 | 105 | 15 | 15 | 0 | 0 | -7 | -105 | 0% | 0
1 | 2016-01-08 | Fri | 08 | 8 | 120 | 15 | 15 | 0 | 0 | -8 | -120 | 0% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 120 | 15 | 0 | 0 | 0 | -8 | -120 | 0% | 0
0 | 2016-01-10 | Sun | 10 | 8 | 120 | 15 | 0 | 0 | 0 | -8 | -120 | 0% | 0
1 | 2016-01-11 | Mon | 11 | 9 | 135 | 15 | 15 | 0 | 0 | -9 | -135 | 0% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 165 | 15 | 15 | 3 | 3 | -10.8 | -162 | 1.818% | 0
1 | 2016-01-13 | Wed | 13 | 12 | 180 | 15 | 15 | 0 | 3 | -11.8 | -177 | 1.667% | 0
1 | 2016-01-14 | Thu | 14 | 13 | 195 | 15 | 15 | 0 | 3 | -12.8 | -192 | 1.538% | 0
1 | 2016-01-15 | Fri | 15 | 14 | 210 | 15 | 15 | 0 | 3 | -13.8 | -207 | 1.429% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 210 | 15 | 0 |  | 3 | -13.8 | -207 | 1.429% | 0
0 | 2016-01-17 | Sun | 17 | 14 | 210 | 15 | 0 |  | 3 | -13.8 | -207 | 1.429% | 0
1 | 2016-01-18 | Mon | 18 | 15 | 225 | 15 | 15 |  | 3 | -14.8 | -222 | 1.333% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 255 | 15 | 15 |  | 3 | -16.8 | -252 | 1.176% | 0
1 | 2016-01-20 | Wed | 20 | 18 | 270 | 15 | 15 |  | 3 | -17.8 | -267 | 1.111% | 0
1 | 2016-01-21 | Thu | 21 | 19 | 285 | 15 | 15 |  | 3 | -18.8 | -282 | 1.053% | 0
1 | 2016-01-22 | Fri | 22 | 20 | 300 | 15 | 15 |  | 3 | -19.8 | -297 | 1% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 300 | 15 | 0 |  | 3 | -19.8 | -297 | 1% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 300 | 15 | 0 |  | 3 | -19.8 | -297 | 1% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 300 | 15 | 15 |  | 3 | -19.8 | -297 | 1% | 0
1 | 2016-01-26 | Tue | 26 | 21 | 315 | 15 | 15 |  | 3 | -20.8 | -312 | 0.9524% | 0
1 | 2016-01-27 | Wed | 27 | 22 | 330 | 15 | 15 |  | 3 | -21.8 | -327 | 0.9091% | 0
1 | 2016-01-28 | Thu | 28 | 23 | 345 | 15 | 15 |  | 3 | -22.8 | -342 | 0.8696% | 0
1 | 2016-01-29 | Fri | 29 | 24 | 360 | 15 | 15 |  | 3 | -23.8 | -357 | 0.8333% | 0
0 | 2016-01-30 | Sat | 30 | 24 | 360 | 15 | 0 |  | 3 | -23.8 | -357 | 0.8333% | 0
0 | 2016-01-31 | Sun | 31 | 24 | 360 | 15 | 0 |  | 3 | -23.8 | -357 | 0.8333% | 0
[7 empty] | 180 | 3 |  | -11.8 | -177 | 1.667%
315
Formulas:
Today = IF([Blue Light]=TODAY(),1,0)

## EQN 30K
| EQN Submission |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 300 |  |  |  | 21
Daily Flow Rate
15
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 15 | 15 | 15 | 0 | 0 | -1 | -15 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 15 | 15 | 0 | 24 | 24 | 0.6 | 9 | 160% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 15 | 15 | 0 | 0 | 24 | 0.6 | 9 | 160% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 30 | 15 | 15 | 14 | 38 | 0.53333 | 8 | 126.7% | 0
1 | 2016-01-05 | Tue | 05 | 3 | 45 | 15 | 15 | 5 | 43 | -0.13333 | -2 | 95.56% | 0
1 | 2016-01-06 | Wed | 06 | 4 | 60 | 15 | 15 | 4 | 47 | -0.86667 | -13 | 78.33% | 0
1 | 2016-01-07 | Thu | 07 | 5 | 75 | 15 | 15 | 21 | 68 | -0.46667 | -7 | 90.67% | 0
1 | 2016-01-08 | Fri | 08 | 6 | 90 | 15 | 15 | 19 | 87 | -0.2 | -3 | 96.67% | 0
0 | 2016-01-09 | Sat | 09 | 6 | 90 | 15 | 0 | 0 | 87 | -0.2 | -3 | 96.67% | 0
0 | 2016-01-10 | Sun | 10 | 6 | 90 | 15 | 0 | 7 | 94 | 0.26667 | 4 | 104.4% | 0
1 | 2016-01-11 | Mon | 11 | 7 | 105 | 15 | 15 | 1 | 95 | -0.66667 | -10 | 90.48% | 0
1 | 2016-01-12 | Tue | 12 | 8 | 120 | 15 | 15 | 1 | 96 | -1.6 | -24 | 80% | 0
1 | 2016-01-13 | Wed | 13 | 9 | 135 | 15 | 15 | 0 | 96 | -2.6 | -39 | 71.11% | 0
1 | 2016-01-14 | Thu | 14 | 10 | 150 | 15 | 15 | 17 | 113 | -2.4667 | -37 | 75.33% | 0
1 | 2016-01-15 | Fri | 15 | 11 | 165 | 15 | 15 |  | 113 | -3.4667 | -52 | 68.48% | 0
0 | 2016-01-16 | Sat | 16 | 11 | 165 | 15 | 0 |  | 113 | -3.4667 | -52 | 68.48% | 0
0 | 2016-01-17 | Sun | 17 | 11 | 165 | 15 | 0 |  | 113 | -3.4667 | -52 | 68.48% | 0
1 | 2016-01-18 | Mon | 18 | 12 | 180 | 15 | 15 |  | 113 | -4.4667 | -67 | 62.78% | 1
1 | 2016-01-19 | Tue | 19 | 13 | 195 | 15 | 15 |  | 113 | -5.4667 | -82 | 57.95% | 0
1 | 2016-01-20 | Wed | 20 | 14 | 210 | 15 | 15 |  | 113 | -6.4667 | -97 | 53.81% | 0
1 | 2016-01-21 | Thu | 21 | 15 | 225 | 15 | 15 |  | 113 | -7.4667 | -112 | 50.22% | 0
1 | 2016-01-22 | Fri | 22 | 16 | 240 | 15 | 15 |  | 113 | -8.4667 | -127 | 47.08% | 0
0 | 2016-01-23 | Sat | 23 | 16 | 240 | 15 | 0 |  | 113 | -8.4667 | -127 | 47.08% | 0
0 | 2016-01-24 | Sun | 24 | 16 | 240 | 15 | 0 |  | 113 | -8.4667 | -127 | 47.08% | 0
1 | 2016-01-25 | Mon | 25 | 17 | 255 | 15 | 15 |  | 113 | -9.4667 | -142 | 44.31% | 0
1 | 2016-01-26 | Tue | 26 | 18 | 270 | 15 | 15 |  | 113 | -10.4667 | -157 | 41.85% | 0
1 | 2016-01-27 | Wed | 27 | 19 | 285 | 15 | 15 |  | 113 | -11.4667 | -172 | 39.65% | 0
1 | 2016-01-28 | Thu | 28 | 20 | 300 | 15 | 15 |  | 113 | -12.4667 | -187 | 37.67% | 0
1 | 2016-01-29 | Fri | 29 | 21 | 315 | 15 | 15 |  | 113 | -13.4667 | -202 | 35.87% | 0
0 | 2016-01-30 | Sat | 30 | 21 | 315 | 15 | 0 |  | 113 | -13.4667 | -202 | 35.87% | 0
0 | 2016-01-31 | Sun | 31 | 21 | 315 | 15 | 0 |  | 113 | -13.4667 | -202 | 35.87% | 0
[7 empty] | 180 | 113 |  | -4.4667 | -67 | 62.78%
Formulas:
Today = IF([EQN Submission]=TODAY(),1,0)

## Delivery 30K
| Delivery |  |  | Goal |  |  |  | Working Days for Month
|  |  |  | 200 |  |  |  | 24
Daily Flow Rate
10
Weekday | Date | Jan. | Calendar | Working Day | Original Daily Goal | Flat Build Plan | 30K Build Plan | 30K Actual | 30K Total Output | Days | PCS | % | Today
1 | 2016-01-01 | Fri | 01 | 1 | 10 | 10 | 10 | 0 | 0 | -1 | -10 | 0% | 0
0 | 2016-01-02 | Sat | 02 | 1 | 10 | 10 | 0 | 0 | 0 | -1 | -10 | 0% | 0
0 | 2016-01-03 | Sun | 03 | 1 | 10 | 10 | 0 | 0 | 0 | -1 | -10 | 0% | 0
1 | 2016-01-04 | Mon | 04 | 2 | 20 | 10 | 10 | 0 | 0 | -2 | -20 | 0% | 0
1 | 2016-01-05 | Tue | 05 | 5 | 50 | 10 | 10 | 0 | 0 | -5 | -50 | 0% | 0
1 | 2016-01-06 | Wed | 06 | 5 | 50 | 10 | 10 | 0 | 0 | -5 | -50 | 0% | 0
1 | 2016-01-07 | Thu | 07 | 6 | 60 | 10 | 10 | 0 | 0 | -6 | -60 | 0% | 0
1 | 2016-01-08 | Fri | 08 | 7 | 70 | 10 | 10 | 20 | 20 | -5 | -50 | 28.57% | 0
0 | 2016-01-09 | Sat | 09 | 8 | 80 | 10 | 0 | 0 | 20 | -6 | -60 | 25% | 0
0 | 2016-01-10 | Sun | 10 | 9 | 90 | 10 | 0 | 0 | 20 | -7 | -70 | 22.22% | 0
1 | 2016-01-11 | Mon | 11 | 10 | 100 | 10 | 10 | 0 | 20 | -8 | -80 | 20% | 0
1 | 2016-01-12 | Tue | 12 | 11 | 110 | 10 | 10 | 0 | 20 | -9 | -90 | 18.18% | 0
1 | 2016-01-13 | Wed | 13 | 11 | 110 | 10 | 10 | 0 | 20 | -9 | -90 | 18.18% | 0
1 | 2016-01-14 | Thu | 14 | 12 | 120 | 10 | 10 | 0 | 20 | -10 | -100 | 16.67% | 0
1 | 2016-01-15 | Fri | 15 | 13 | 130 | 10 | 10 |  | 20 | -11 | -110 | 15.38% | 0
0 | 2016-01-16 | Sat | 16 | 14 | 140 | 10 | 0 |  | 20 | -12 | -120 | 14.29% | 0
0 | 2016-01-17 | Sun | 17 | 15 | 150 | 10 | 0 |  | 20 | -13 | -130 | 13.33% | 0
1 | 2016-01-18 | Mon | 18 | 16 | 160 | 10 | 10 |  | 20 | -14 | -140 | 12.5% | 1
1 | 2016-01-19 | Tue | 19 | 17 | 170 | 10 | 10 |  | 20 | -15 | -150 | 11.76% | 0
1 | 2016-01-20 | Wed | 20 | 17 | 170 | 10 | 10 |  | 20 | -15 | -150 | 11.76% | 0
1 | 2016-01-21 | Thu | 21 | 18 | 180 | 10 | 10 |  | 20 | -16 | -160 | 11.11% | 0
1 | 2016-01-22 | Fri | 22 | 19 | 190 | 10 | 10 |  | 20 | -17 | -170 | 10.53% | 0
0 | 2016-01-23 | Sat | 23 | 20 | 200 | 10 | 0 |  | 20 | -18 | -180 | 10% | 0
0 | 2016-01-24 | Sun | 24 | 20 | 200 | 10 | 0 |  | 20 | -18 | -180 | 10% | 0
1 | 2016-01-25 | Mon | 25 | 20 | 200 | 10 | 10 |  | 20 | -18 | -180 | 10% | 0
1 | 2016-01-26 | Tue | 26 | 20 | 200 | 10 | 10 |  | 20 | -18 | -180 | 10% | 0
1 | 2016-01-27 | Wed | 27 | 20 | 200 | 10 | 10 |  | 20 | -18 | -180 | 10% | 0
1 | 2016-01-28 | Thu | 28 | 21 | 210 | 10 | 10 |  | 20 | -19 | -190 | 9.524% | 0
1 | 2016-01-29 | Fri | 29 | 22 | 220 | 10 | 10 |  | 20 | -20 | -200 | 9.091% | 0
0 | 2016-01-30 | Sat | 30 | 23 | 230 | 10 | 0 |  | 20 | -21 | -210 | 8.696% | 0
0 | 2016-01-31 | Sun. | 31 | 24 | 240 | 10 | 0 |  | 20 | -22 | -220 | 8.333% | 0
[7 empty] | 120 | 20 |  | -10 | -100 | 16.67%
Formulas:
Today = IF([Delivery]=TODAY(),1,0)

## Gemba QCPC (hidden)
[6 empty] | Impedance | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 Total
[6 empty] | Manpower Issues | 3 | 2 | 3 | 2 | 2 | 2 | 7 | 2 | 4 | 3 | 2 | 2 | 34
[6 empty] | Goodrich TAT | 2 | 4 | 3 | 1 | 4 | 7 |  | 7 | 6 | 3 | 4 | 4 | 45
[6 empty] | Coating Recycle | 7 | 2 | 4 | 7 | 7 | 3 | 7 | 7 | 3 | 3 | 6 | 6 | 62
[6 empty] | Flow / Capacity | 2 | 4 | 2 | 2 | 2 | 4 | 7 | 4 | 4 | 6 | 4 | 4 | 45
[6 empty] | Quality Issue | 2 | 2 | 4 | 3 | 3 | 7 | 5 | 7 | 2 | 3 | 3 | 3 | 44
[6 empty] | Weld Recycle | 7 | 4 | 2 | 2 | 3 | 2 | 4 | 7 | 6 | 2 | 2 | 2 | 43
[6 empty] | Goodrich Recycle | 7 | 2 | 7 | 3 | 2 | 6 | 6 | 6 | 6 | 2 | 7 | 7 | 61
[6 empty] | Down Machine | 2 | 4 | 2 | 3 | 3 | 4 | 2 | 2 | 2 | 4 | 2 | 2 | 32
[6 empty] | Purchasing | 4 | 6 | 5 | 6 | 7 | 8 | 9 | 7 | 6 | 8 | 4 | 4 | 74
Project # | Turnback | Targeted Initiative | Owner(s) | Planned Finish Date | Status
1
2
3